## Sheet1
Tasks and Assignment Breakdown
| Group: | TBD
| Team Members (and initials): | Mikayla Campbell (MC), Joseph Goh (JG), Olivia Pannell (OP), Bethany Van Meter (BVM), Ben Verney (BV)
| Date this was last updated: | 2020-01-13
| Last updated by (whom): | JG
In general, you should archive a copy of this spreadsheet (with the date in the file name in mmddyy format) before modifying it.
| Names to be chosen from: | all staff | (whoever attended) | MC | JG | OP | BVM | BV
| Statuses to be chosen from: | completed | not yet completed
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1
| Group meeting. | completed | all staff | 2020-01-10 | 1 | 2020-01-13 | 2020-01-13 | all staff | 1 | JG | 2020-01-13
| Create a shared repository | completed | JG | 2020-01-13 | 0 | 2020-01-13 | 2020-01-13 | JG | 0 | all staff | 2020-01-13 | Link: https://github.com/sceotere/uoregon-cis422-p1
| Establish weekly meeting schedule. Post on shared repository. | completed | all staff | 2020-01-13 | 0 | 2020-01-13 | 2020-01-13 | all staff | 0 | JG | 2020-01-13
| Outline week 1 progress in project plan | not yet completed | all staff | 2020-01-13 |  | 2020-01-13
| Finish initial list of project requirements | not yet completed | all staff | 2020-01-13 |  | 2020-01-14
| Group meeting. | not yet completed | all staff | 2020-01-13 |  | 2020-01-14
| Write first draft of SRS | not yet completed | BVM | 2020-01-13 |  | 2020-01-16
| Group meeting. | not yet completed | all staff | 2020-01-10 |  | 2020-01-16
Week 2