## Sheet1
Tasks and Assignment Breakdown
| Group: | TBD
| Team Members (and initials): | Mikayla Campbell (MC), Joseph Goh (JG), Olivia Pannell (OP), Bethany Van Meter (BVM), Ben Verney (BV)
| Date this was last updated: | 2020-01-14
| Last updated by (whom): | BVM
In general, you should archive a copy of this spreadsheet to the github repo (with the date in the file name in mmddyy format) before modifying it.
| Names to be chosen from: | all staff | (whoever attended) | MC | JG | OP | BVM | BV
| Statuses to be chosen from: | completed | not yet completed
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1
| Group meeting. | completed | all staff | 2020-01-10 | 1 | 2020-01-13 | 2020-01-13 | all staff | 1 | JG | 2020-01-13
| Group meeting. | not yet completed | all staff | 2020-01-10 |  | 2020-01-16
| Create a shared repository | completed | JG | 2020-01-13 | 0 | 2020-01-13 | 2020-01-13 | JG | 0 | all staff | 2020-01-13 | Link: https://github.com/sceotere/uoregon-cis422-p1
| Establish weekly meeting schedule. Post on shared repository. | completed | all staff | 2020-01-13 | 0 | 2020-01-13 | 2020-01-13 | all staff | 0 | JG | 2020-01-13
| Outline week 1 progress in project plan | not yet completed | all staff | 2020-01-13 |  | 2020-01-13
| Finish initial list of project requirements | not yet completed | all staff | 2020-01-13 |  | 2020-01-14
| Group meeting. | not yet completed | all staff | 2020-01-13 |  | 2020-01-16
| Write first draft of SRS | completed | BVM | 2020-01-13 | 6 | 2020-01-16 | 2020-01-14 | BVM | 7
| Write currently recorded project plan details into formatted document | completed | JG | 2020-01-14 | 1 | 2020-01-14 | 2020-01-14 | JG | 2
| Write first draft of SDS | not yet completed | MC | 2020-01-14 | 6 | 2020-01-16
| Complete SRS/SDS/Project reqs | not yet completed | all staff | 2020-01-14 | 3 | 2020-01-16
Week 2